## Example
Sprint Backlog
***หมายเหตุ: กำหนดให้แต่ละ Sprint มีความยาว 1 สัปดาห์เท่ากัน
Sprint No. | Product Backlog Items | Sprint Tasks | Details in Task | Initial Estimate of Effort | New Estimate of Effort Remaining at The End of Day…
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Team velocity = | 114.5 | [8 empty] | Burrn down charts:
1 | As a student, I want to view my course list and exam schedule via a user-friendly interface so that I can easily plan my study and exam preparation. | Task1 | Wireframe UI mockup | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0
|  | Task2 | Database design | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 122 |  | DAYS | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  | Task3 | Database setup | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | HOURS | 78 | 78 | 64 | 38 | 38 | 38 | 0
|  | Task4 | Forntent Login | 14 | 14 | 14 | 14 | 0 | 0 | 0 | 0
|  | Task5 | Forntent Homepage | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0
|  | Task6 | Frontend หน้ารายการวิชา | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0
|  | Task7 | Forntent ตารางเรียน ตารางสอบ | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0
|  | Task8 | Frontend รายละเอียดวิชา | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0
|  | Task9 | Frontend ค้นหาวิชา | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  | Task10 | Backend Login 1. Login 2. Login with SSO 3. Login with ThaiD | 38 | 0 | 0 | 38 | 38 | 38 | 38 | 0
2 | As a student, I want to securely log in and retrieve accurate course and exam data so that I can reliably access my academic information. | Task11 | Backend แสดงรายละเอียด + รหัสวิชา 1. ค้นหารายวิชา 2. แสดงข้อมูลรายวิชาทั้งหมดจากรหัสนักศึกษา 3. แสดงรายละเอียดวิชาจากรหัสวิชา | 38 | 38 | 38 | 38 | 0 | 0 | 0 | 0
|  | Task12 | Testing Automate UAT | 33 | 33 | 33 | 33 | 33 | 0 | 0 | 0 | 107 |  | DAYS | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  | Task13 | Bug Fixing | 25 | 0 | 0 | 0 | 25 | 25 | 0 | 0 |  |  | HOURS | 71 | 71 | 71 | 58 | 32 | 11 | 4
|  | Task14 | Document เอกสาร | 4 | 0 | 0 | 0 | 0 | 4 | 4 | 0
|  | Task15 | Document คู่มือ | 3 | 0 | 0 | 0 | 0 | 3 | 3 | 0
|  | Task16 | Deployment | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 4